## Projected
WP | Task | May | June | July | August | September | October | November | 6th Dec | 13th Dec | 20th Dec | 27th Dec | 3rd Jan | 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 7th Mar | 14th Mar | 21st Mar | 28th Mar | 4th Apr | 11th Apr | 18th Apr | 25th Apr | 2nd May | 9th May | 16th May | 23rd May | 30th May | 6th Jun | 13th Jun
SOI | SOI Research
SOI Submission
SOI Waiting Approval
SOI Approved
Meeting | Mentor Meeting
Report
Create an account
Load template
Read guidelines
Deliverables
Share with lecturer
Commit regularly
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report
Literature Review
Review datasets / assets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Find tutorial / Review existing games
Replicate tutorial
Create custom dataset / assets
Develop prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract